## Sprint 1
Sprint: | 1
Start Date: | 24 Febuary, 2020
Finish Date: | 28 Febuary, 2020
User Stories Backlog | Exp | Part 1 | Part 2 | Part 3 | Part 4 | In Progress | Finished |  |  |  | Testing
As a user, I would like a login to make the App Secure and Safe | 2 | [5 empty] | Create Login Form | Connect Login Form to Database | Check If login details are correct | Error Messages | Tested, All working
As a Programmer I would like a Database to store all the data in | 2 | [5 empty] | Create Database | Create Tables | Create Test Data |  | Tested, All working
As a user I would like a Main page that comes up once I have logged in | 1 | [5 empty] | Create Main Page | Link Main Page too the Login Page |  |  | Tested, All working

## Sprint 2
Sprint: | 2
Start Date: | 2020-03-02
Finish Date: | 2020-03-06
User Stories Backlog | Exp | Part 1 | Part 2 | Part 3 | Part 4 | In Progress | Finished |  |  |  | Testing
As a User I would like to have my sections displayed on the main page | 1 | [5 empty] | Create Panel for sections to be displayed on | Read out sections from database | Display sections | Read out clicked buttons | Tested, All working
As a User I would like to add Sections too my orchard | 2 | [5 empty] | Create 'Add Section' Form | Add controls too Add Section Form | Add 'Add Section' button too Main form | Save New Sections too Database | Tested, All working
As a User I would like to be able to save my orchard map and see it on the main page | 2 | [5 empty] | Make upload button | Link too database | Make map load onto main page |  | Tested, All working

## Sprint 3
Sprint: | 3
Start Date: | 2020-03-09
Finish Date: | 2020-03-15
User Stories Backlog | Exp | Part 1 | Part 2 | Part 3 | Part 4 | In Progress | Finished |  |  | Testing
As a user I would like to view my actions | 1 | [5 empty] | Get data from database | Make new form | Display data on form | Tested, All working
As a programmer I would like to have an Action class | 1 | [5 empty] | Make Action Class |  |  | Tested, All working
As a user I would like to view each action individually | 2 | [5 empty] | Make a new form | Retrieve data from database | Display data on form | Tested, All working
As a User I would like to edit actions | 1 | [5 empty] | Validate data | Update exisitng entry in database |  | Tested, All working

## Sprint 4
Sprint: | 4
Start Date: | 2020-03-16
Finish Date: | 2020-03-20
User Stories Backlog | Exp | Part 1 | Part 2 | Part 3 | Part 4 | In Progress | Finished |  |  | Testing
As a user I would like to view my harvests | 1 | [5 empty] | Get data from database | Make new form | Display data on form | Tested, All working
As a programmer I would like to have an Harvests class | 1 | [5 empty] | Make Harvest Class |  |  | Tested, All working
As a user I would like to view each harvest individually | 2 | [5 empty] | Make a new form | Retrieve data from database | Display data on form | Tested, All working
As a User I would like to edit harvests | 1 | [5 empty] | Validate data | Update exisitng entry in database |  | Tested, All working

## Sprint 5
Sprint: | 5
Start Date: | 2020-05-04
Finish Date: | 2020-05-08
User Stories Backlog | Exp | Part 1 | Part 2 | Part 3 | Part 4 | In Progress | Finished |  |  |  | Testing
As a user I would like to add new harvests | 2.5 | [5 empty] | Create 'Add Harvests' Form | Add controls too Add Harvests Form | Add 'Add Harvests' button too Main form | Save New Harvest too Database | Tested, All working
As a user I would like to add new actions | 2.5 | [5 empty] | Create 'Add Action' Form | Add controls too Add Action Form | Add 'Add Action' button too Main form | Save New Action too Database | Tested, All working

## Sprint 6
Sprint: | 6
Start Date: | 2020-05-11
Finish Date: | 2020-05-15
User Stories Backlog | Exp | Part 1 | Part 2 | Part 3 | Part 4 | In Progress | Finished |  |  | Testing
As a user I would like to be able to edit sections | 1 | [5 empty] | Create new form | Validate data | update data to exisitng entry | Tested, All working
As a user I would like the interface to be easy to use | 4 | [5 empty] | Redesign interface | Implement redesign of interface |  | Tested, All working

## Sprint 7
Sprint: | 7
Start Date: | 2020-05-18
Finish Date: | 2020-05-22
User Stories Backlog | Exp | Part 1 | Part 2 | Part 3 | Part 4 | In Progress | Finished |  |  | Testing
As a programmer I would like all SQL queries to be injection proof | 5 | [5 empty] | Identify all pieces of code at risk | write piece of code to make sql injection proof | Implement code within all at risk pieces of code | Tested, All working